## Jira Export Excel CSV (all fiel
Summary | Issue key | Issue id | Issue Type | Status | Project name | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Creator | Created | Resolved | Description | Watchers | Attachment | Custom field (Actual Result) | Sprint | Custom field (Story point estimate) | Parent | Parent summary
Missing Figma Design for "Like Public Task" Feature | TTP-25 | 10099 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 20:56 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0, Figma Design – Public task Screens * *Location:* User Story #17, "Like Public Task" * *Description:* The user story specifies that users should have the ability to *like a public task* as a way to express appreciation or agreement. However, the current Figma design does not include any screen design or interaction element for liking a public task. ** Missing UI components (e.g., a *"Like" button*) to allow users to like a task. ** No design showing the *"Like" count* incrementing when the user likes a task. *Impact:* # Without a proper design for this feature, the development team may be unclear on how the *like interaction* should be visually represented or function. This could lead to inconsistent implementation or delays. | Alaa Radwan | 16/Sep/24 8:56 PM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;w1.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10034 |  | Pre-Testing Activities | 3 | 10173 | Public task management
Missing Design Elements for Language Change Functionality in User Story #14 (Change App Language from Arabic to English) | TTP-24 | 10089 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 02:36 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* Figma Design – Change App Language ---- *Location:* User Story #14, "Change App Language from Arabic to English" *Issue Description:* The Figma design does not include visual representations for the acceptance criteria related to changing the application language from Arabic to English. This omission affects the ability to effectively verify and test the functionality. *Current Acceptance Criteria:* # *Language Settings Option:* #* *Given* I am using the application in Arabic, #* *When* I navigate to the settings or preferences section, #* *And* I look for the language settings, #* *Then* I should see an option to change the language. # *English as a Language Option:* #* *Given* I select the option to change the language, #* *When* I see the list of available languages, #* *Then* English should be one of the options listed. # *Switching to English:* #* *Given* I select English as the preferred language, #* *When* I confirm my selection, #* *Then* the language of the entire application interface should switch to English immediately. # *English Language Display:* #* *Given* the language is changed to English, #* *When* I navigate through the application's menus and screens, #* *Then* all text, labels, and prompts should be displayed in English. # *Switching Back to Arabic:* #* *Given* I want to switch back to Arabic, #* *When* I navigate to the language settings again, #* *Then* I should be able to select Arabic as the language option, and the interface should switch back to Arabic accordingly. *Impact* Including these design elements is essential for validating the user story’s acceptance criteria and ensuring the application supports language changes as specified. It ensures that both language transitions are implemented and tested correctly. | Alaa Radwan | 16/Sep/24 2:36 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;16.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10025 |  | Pre-Testing Activities | 3 | 10170 | Language switching
Missing Design Elements for Language Change Functionality in User Story #13(Change App Language from English to Arabic) | TTP-23 | 10088 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 02:24 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* Figma Design – Change App Language v1.0 *Location:* User Story #13, "Change App Language from English to Arabic" *Issue Description:* The Figma design does not include visual representations for the acceptance criteria related to changing the application language from English to Arabic. This lack of design coverage impacts the ability to verify and test the functionality effectively. *Current Acceptance Criteria:* # *Language Settings Option:* #* *Given* I am using the application in English, #* *When* I navigate to the settings or preferences section, #* *And* I look for the language settings, #* *Then* I should see an option to change the language. # *Arabic as a Language Option:* #* *Given* I select the option to change the language, #* *When* I see the list of available languages, #* *Then* Arabic should be one of the options listed. # *Switching to Arabic:* #* *Given* I select Arabic as the preferred language, #* *When* I confirm my selection, #* *Then* the language of the entire application interface should switch to Arabic immediately. # *Arabic Language Display:* #* *Given* the language is changed to Arabic, #* *When* I navigate through the application's menus and screens, #* *Then* all text, labels, and prompts should be displayed in Arabic. # *Switching Back to English:* #* *Given* I want to switch back to English, #* *When* I navigate to the language settings again, #* *Then* I should be able to select English as the language option, and the interface should switch back to English accordingly. *Impact:* Including these design elements is crucial for validating the user story’s acceptance criteria and ensuring the application supports language changes as specified. It helps ensure that the functionality is implemented and tested correctly. | Alaa Radwan | 16/Sep/24 2:24 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;15.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10024 |  | Pre-Testing Activities | 3 | 10170 | Language switching
Missing Design Elements for Logout Functionality in User Story #12(Logout ) | TTP-21 | 10086 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:48 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Document Reference:* Figma Design – Logout Process v1.0 *Finding:* *Location:* User Story #12, "Logout " *Issue Description:* The Figma design does not include the following key elements for the logout process: # *Confirmation Page/Message:* There is no design for a confirmation page or message to inform the user that they have successfully logged out. # *Navigation After Logout:* There is no design specifying that if a user tries to access any page while logged out, they should be navigated back to the login page. *Suggested Acceptance Criteria:* # *Logout Confirmation:* #* *Design:* Include a confirmation page or message that displays after the user logs out, confirming the successful logout. For example, a message like "You have been logged out successfully." # *Post-Logout Navigation:* #* *Design:* Ensure that if the user tries to access any page that requires authentication after logging out, they are redirected to the login page. *Impact:* Including these design elements is crucial for providing a clear and user-friendly logout experience. | Alaa Radwan | 16/Sep/24 1:48 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;13.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10022 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing Error Message Screen Design for Invalid Image Format or Exceeded Size Limit in "Change Account Image" | TTP-19 | 10084 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:29 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Document Reference:* User Stories Document – v1.0, Figma Design * *Location:* User Story #11, "Change Account Image" * *Description:* The user story specifies that an error message should be displayed if the user attempts to upload an image that is in an invalid format (e.g., not JPG or PNG) or exceeds the allowed file size. However, the Figma design for the *Change Account Image* screen does not include the necessary *error message designs* for these scenarios. ** Missing error message for *invalid image format* (e.g., when a user uploads a GIF or BMP file). ** Missing error message for *exceeded file size limit* (e.g., when the image is larger than the allowed size, such as 5MB). *Suggested Correction:* # Add screen designs to the Figma file that handle the following error scenarios: ## *Invalid Image Format* ## *Exceeded File Size* | Alaa Radwan | 16/Sep/24 1:29 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;11.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10020 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing Navigation Screen Design for Redirecting to Login After Password Change | TTP-18 | 10083 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:18 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0, Figma Design ---- # *Location:* User Story #10, "Change Account Password" # *Description:* The user story mentions that after successfully changing the password, the user must log in again using the new password. However, the Figma design is missing a *screen that guides the user to the login page* after the password change process is completed. #* The design should include a *navigation screen* or message that explains the need to log in again and provides a link or button to the login screen. # *Impact:* #* Without clear instructions or navigation after a successful password change, users may not understand that they need to log in again with the new password, which could result in confusion or frustration. A well-designed navigation flow ensures the user smoothly transitions from the password change process back to logging in. # *Suggested Correction:* #* Add a *screen design* that appears after the password has been successfully changed, informing the user that they will need to log in again with their new password. | Alaa Radwan | 16/Sep/24 1:18 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;9.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10019 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing Confirmation Screen Design for Successful Password Change in "Change Account Password" | TTP-17 | 10082 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:15 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Location:* User Story #10, "Change Account Password" * *Description:* The user story specifies that after successfully changing the password, the user should receive a *confirmation message* indicating that the password has been updated. However, the current Figma design for the *Change Account Password* screen does not include a *confirmation screen* or message for successful password changes. ** The absence of this confirmation screen may leave users uncertain about whether their action was completed successfully. # *Suggested Correction:* #* Add a *confirmation screen* design to the Figma file, which should be displayed after the password is changed successfully. #* The confirmation message should clearly state that the password has been updated and may include a button or link to return to the dashboard or account settings. | Alaa Radwan | 16/Sep/24 1:15 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;8.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10018 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing Error Message Screen Design for Invalid Password Entry in "Change Account Password" | TTP-16 | 10081 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:12 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0, Figma Design – Edit profile Screen * *Location:* User Story #10, "Change Account Password" * *Description:* The user story specifies that when the user enters an invalid current password or when the new password does not meet the required criteria, an *error message* should be displayed. However, the Figma design for the *Change Account Password* screen does not include the corresponding error message screens for these scenarios. ** There is no design for the error state when the user inputs an incorrect current password. ** There is no design for the error state when the new password does not meet the required criteria (e.g., length, special characters). * *Impact:* ** Without a proper design for these error messages, the development team may implement inconsistent or unclear error handling, leading to a poor user experience. Properly designed error messages are essential for guiding the user in correcting their inputs. * *Suggested Correction:* ** Add screen designs to the Figma file for the following scenarios: **# *Error Message for Invalid Current Password* **# *Error Message for Invalid New Password* | Alaa Radwan | 16/Sep/24 1:12 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;7.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10017 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing Acceptance Criteria for "Task Confirmation Screen" in User Stories for Repeated Tasks (Weekly, Monthly, Yearly) | TTP-12 | 10077 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:22 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0, Figma Design ---- h3. *Finding:* # *Location:* User Story #6 ("Create a New Weekly Task"), User Story #7 ("Create a New Monthly Task"), User Story #8 ("Create a New Yearly Task") # *Description:* The *"Task Confirmation Screen"* is mentioned in the Figma design, but there is no corresponding *acceptance criteria* in the user stories for weekly, monthly, or yearly tasks. # *Suggested Correction:* #* Add acceptance criteria for the *Task Confirmation Screen* in the relevant user stories for creating repeatable tasks. #* Example Acceptance Criteria for User Story #6 (Weekly Task): #** *Given* that the user has completed the task details for a weekly task #** *When* the user clicks "Submit" #** *Then* the app should display a *Task Confirmation Screen* showing the task title, frequency, and any additional details #** *When* the user confirms the task details on the confirmation screen #** *Then* the app should create the task and display it on the user's dashboard. | Alaa Radwan | 16/Sep/24 12:22 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;3.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10013 |  | Pre-Testing Activities | 3 | 10165 | Task management system
Missing "Task Type" (Public/Private) Option in Task Creation User Stories | TTP-10 | 10075 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:06 | 2024-11-09 11:46 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Location:* User Story #5 ("Create a New One-Time Task"), User Story #6 ("Create a New Weekly Task"), User Story #7 ("Create a New Monthly Task"), and User Story #8 ("Create a New Yearly Task") * *Issue Description:* The user stories for creating one-time, weekly, monthly, and yearly tasks do not specify the option for setting the task type as *Public or Private*. This feature is appearing in the figma design and didn’t mentioned in the user stories. * *Suggested Correction:* Update the user stories for task creation to include acceptance criteria for selecting the *Task Type (Public or Private)*. For example, in User Story #5, add: ** *Acceptance Criteria:* *** Given that the user is creating a new task *** When the task creation form is displayed *** Then there should be an option to set the task as *Public* or *Private* *** When the user selects *Public*, the task should be visible to all users *** When the user selects *Private*, the task should only be visible to the task creator. | Alaa Radwan | 16/Sep/24 12:06 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;1.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10011 |  | Pre-Testing Activities | 3 | 10173 | Public task management
Missing Acceptance Criteria for Error Handling- user story "Create a New One Time Task" | TTP-8 | 10073 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 02:28 | 2024-11-09 11:46 | *Date:* September 14, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 *Description:* The design specifies that if the user does not enter information in required fields, an error message should prompt the user to "Please enter the title and date." However, the acceptance criteria for this behavior are missing in the user story. *Current Design Reference:* * Error message: "Please enter the title and date" when required fields are left empty. *Suggested Acceptance Criteria:* *Error Message Display:* If the user attempts to create a new one-time task without entering required information in the title and date fields, the system must display an error message. *Impact:* Including these acceptance criteria is essential for ensuring that the user interface behaves as expected and provides clear feedback when required fields are not completed. This will enhance user experience and prevent incomplete task creation. | Alaa Radwan | 14/Sep/24 2:27 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;17a.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10008 |  | Pre-Testing Activities | 3 | 10165 | Task management system
Review of User Stories – Missing First and Last Name Fields in User Registration | TTP-2 | 10067 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 00:49 | 2024-11-09 11:46 | *Date:* September 13, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 *Summary:* During the static review of the *User Registration* user story, it was identified that the user story does not specify fields for capturing *First Name* and *Last Name* during the registration process. These fields are typically essential for user identification and should be included in the user registration workflow. *Description:* The user story omits the requirement for *First Name* and *Last Name* input fields in the registration process. Without explicitly mentioning these fields, the development team might overlook capturing these critical details, which are necessary for building a comprehensive user profile. * *Impact:* ** User registration could miss key identity fields, potentially leading to gaps in user data management. ** Future functionalities that rely on the user's full name (e.g., personalization, emails, account recovery) may be affected. * *Suggested Solution:* ** Update the "User Registration" user story to include acceptance criteria for capturing *First Name* and *Last Name* fields. ** Ensure that these fields are marked as either optional or mandatory, depending on stakeholder requirements. | Alaa Radwan |  |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Review of User Registration Screen – Missing First and Last Name Fields | TTP-1 | 10066 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 00:44 | 2024-11-09 11:46 | *Date:* September 13, 2024 *Reviewed By:* Alaa Radwan *Design Reference:* Figma File – User Registration Screen. *Summary:* During the static review of the Figma design for the User Registration screen, it was observed that the fields for *First Name* and *Last Name* are missing, which are critical for capturing user identity information. * *Impact:* ** User identity might not be adequately captured. ** This could lead to confusion or a poor user experience when a more detailed profile is required later. * *Suggested Solution:* ** Add *First Name* and *Last Name* input fields to the registration form. ** Confirm with stakeholders if these fields should be mandatory. | Alaa Radwan | 14/Sep/24 2:09 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;11.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10006 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing "When" Step in Acceptance Criteria for Browser Back Button After Logout | TTP-39 | 10113 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-17 02:00 | 2024-09-17 22:52 | *Date:* September 17, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Description:* In the acceptance criteria: ** *"Given I am logged out of my account, And I try to use the browser's back button to return to a previously visited page,* ** *Then I should not be able to access any secured pages or sensitive information without logging back in."* * The *"When"* step is missing, which would clarify the user's action of trying to navigate back to a previously visited page. This step is crucial for defining the exact action that should be restricted. * *Suggested Correction*: ** *Given* I am logged out of my account, ** *When* I try to use the browser's back button to return to a previously visited page, ** *Then* I should not be able to access any secured pages or sensitive information without logging back in. | Alaa Radwan |  |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing "When" Step in Acceptance Criteria for User Login | TTP-32 | 10106 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-17 01:36 | 2024-09-17 22:52 | *Date:* September 17, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Description:* In the acceptance criteria: ** *"Given that the user successfully logs in,* ** *Then the app should redirect the user to their dashboard where they can access personalized content."* * The *"When"* step is missing. The *"When"* clause is necessary to define the action that causes the app to redirect the user to the dashboard after a successful login. *Suggested Correction:* * *Given* that the user successfully logs in, * *When* the login authentication is complete, * *Then* the app should redirect the user to their dashboard where they can access personalized content. | Alaa Radwan | 17/Sep/24 1:36 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;1.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10037 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Missing "When" Step in Acceptance Criteria for User Registration | TTP-30 | 10104 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-17 01:22 | 2024-09-17 22:52 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Description:* In the acceptance criteria: ** *"Given that the user account is successfully created,* ** *Then the app should automatically log in the user and redirect them to their dashboard."* * The *"When"* step is missing. The absence of the *"When"* clause makes it unclear when exactly the app should log in the user and redirect them to their dashboard. * *Impact:* ** This missing step can lead to confusion regarding the conditions under which the app should automatically log in the user and proceed with the redirection. It breaks the standard *Given-When-Then* structure, reducing clarity for developers and testers. * *Suggested Correction:* ** *Given* that the user account is successfully created, ** *When* the account creation process is completed, ** *Then* the app should automatically log in the user and redirect them to their dashboard. | Alaa Radwan | 17/Sep/24 1:22 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;eee.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10036 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Incorrect Word "Join" in Public Task Screen, Should Be "Follow" according to the user story #19 | TTP-26 | 10100 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 21:14 | 2024-09-17 22:52 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Design Reference:* Figma File – Public Tasks Screen * *Description:* The Figma design for the *Public Task* screen incorrectly uses the word *"Join"* when referring to user interaction with public tasks. According to the user stories, the correct interaction should be to *"Follow"* a public task or user, not "Join." ** The button labeled "*Join*" is misleading, as users are intended to follow tasks for updates rather than actively joining them. | Alaa Radwan | 16/Sep/24 9:14 PM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;ee.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10035 |  | Pre-Testing Activities | 3
Missing "When" Condition in Logout Acceptance Criteria | TTP-22 | 10087 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:51 | 2024-09-17 22:52 | *Date:* September 16, 2024 *Reviewed By:*Alaa Radwan *Document Reference:* User Stories Document – v1.0 *Finding:* *Location:* User Story #12, "Logout " *Issue Description:* The acceptance criteria for the logout functionality are missing the "When" condition. | Alaa Radwan | 16/Sep/24 1:51 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;14.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10023 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Typo in Figma Design for "Change account Image" Screen | TTP-20 | 10085 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 01:36 | 2024-09-17 22:52 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* Figma Design – Change Image Screen *Finding:* *Location:* Change Image Screen *Issue Description:* In the Figma design for the "Change Image" screen, the text "Take" is incorrectly written as "Tack." This typographical error needs correction to ensure clarity and professionalism. *Current Text:* * "Tack picture" *Corrected Text:* * "Take picture" | Alaa Radwan | 16/Sep/24 1:36 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;12.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10021 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Incorrect Use of "I" Instead of "The User" in Acceptance Criteria from "Change Account Password" to the End of the Document | TTP-15 | 10080 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:49 | 2024-09-17 22:51 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 ---- # *Location:* User Stories #10 ("Change Account Password") to #19 ("Follow Other Users") # *Description:* In the acceptance criteria for the user stories starting from *"Change Account Password"* to the end of the document, the pronoun *"I"* is used instead of the more formal and consistent *"The user."* #* Example: *"Given I input my current password incorrectly"* should be *"Given the user inputs their current password incorrectly."* # *Impact:* #* The use of *"I"* breaks consistency with the rest of the document, where *"The user"* is used to describe actions in the third person. This inconsistency in pronoun usage may lead to confusion and could affect the uniformity of the document's tone and style. # *Suggested Correction:* #* Replace all instances of *"I"* in the acceptance criteria with *"The user"* to maintain consistency with the rest of the user stories. #* Example Correction: #** Change from: *"Given I input my current password incorrectly"* #** To: *"Given the user inputs their current password incorrectly."* | Alaa Radwan | 16/Sep/24 12:49 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;6.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10016 |  | Pre-Testing Activities | 3
Inconsistent Formatting for "When" in Weekly Task User Story | TTP-14 | 10079 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:32 | 2024-09-17 22:51 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Location:* User Story #6, "Create a New Weekly Task" * *Description:* In the sentence *"When the user submits the task,"* the word "*When*" is not bolded or colored, unlike other key phrases such as "*Given*" and "*Then*" in the user stories. This inconsistency in formatting may disrupt readability and lead to confusion. * *Suggested Correction:* ** Update the sentence to bold and color the word "*When*" to maintain consistency with other formatted phrases in the user stories. The corrected sentence should be: **"When* the user submits the task," | Alaa Radwan | 16/Sep/24 12:32 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;5.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10015 |  | Pre-Testing Activities | 3
Incorrect Titles "Repeatable Task Frequency" and "Weekly Task Information" in One-Time Task Design | TTP-13 | 10078 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:26 | 2024-09-17 22:50 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Design Reference:* Figma File – One-Time Task ---- # *Location:* Figma Design for One-Time Task Creation Screen # *Description:* The titles *"Repeatable Task Frequency"* and *"Weekly Task Information"* are incorrectly placed under the *One-Time Task* design. These titles are relevant to repeatable tasks (weekly) and should not be present in the design for one-time tasks. # *Impact:* #* This could confuse users during task creation, as they may expect options for repeatable tasks when they are only setting up a one-time task. The inconsistency between the task type and the titles may lead to a poor user experience. # *Suggested Correction:* #* Remove the titles *"Repeatable Task Frequency"* and *"Weekly Task Information"* from the *One-Time Task* creation screen in the Figma design. #* Ensure these titles are only included in the relevant sections for creating weekly tasks. | Alaa Radwan | 16/Sep/24 12:26 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;4.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10014 |  | Pre-Testing Activities | 3
Missing Titles "Repeatable Task Frequency" and "Weekly Task Information" in adding repeatable task in figma Design | TTP-11 | 10076 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-16 00:12 | 2024-09-17 22:50 | *Date:* September 16, 2024 *Reviewed By:* Alaa Radwan *Design Reference:* Figma File – adding repeatable task ---- h3. *Finding:* # *Location:* Figma Design for Task Creation Screen (Weekly Task) # *Description:* The *titles "Repeatable Task Frequency"* and *"Weekly Task Information"* are missing in the Figma design for the weekly task. # *Suggested Correction:* #* Add a clear title, "*Repeatable Task Frequency*," at the top of the section where the user selects how often the task will repeat. #* Add another title, "*Weekly Task Information*," above the fields where users input specific details for their weekly tasks. | Alaa Radwan | 16/Sep/24 12:12 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;2.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10012 |  | Pre-Testing Activities | 3
Inconsistent Terminology: "Click" vs. "Tap" | TTP-7 | 10072 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 02:08 | 2024-09-17 22:48 | *Date:* September 14, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document *Finding:* *Location:* User Story , "*Create a New One Time Task*" *Issue Description:* In the user story, the term "click" is used to describe user interactions on a mobile app. For mobile devices, the term "tap" is more appropriate as it reflects the actual user action. *Current Text:* * "*Given* that the user clicks on the option to create a new task " *Suggested Correction:* Update the user story to use the term "tap" to accurately describe mobile interactions. Be sure that using the term “Tap“ in all the others user stories. *Impact:* Using the correct terminology ensures clarity and consistency in the user stories, helping to avoid confusion during development and ensuring that interactions are described accurately. | Alaa Radwan | 14/Sep/24 2:07 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;16.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10005 |  | Pre-Testing Activities | 3
Review of login Screens – Presence of Two Different Logo shapes in Login Screens | TTP-6 | 10071 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 01:37 | 2024-09-17 22:48 | *Date:* September 14, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* Figma Design – Login Screens *Description:* The Figma design files for the login screens currently feature two different shape logos across the two screens. This inconsistency can create confusion for developers. *Current Logos:* * *Login Screen A:* Logo is small and cotrasted than the background * *Login Screen B:* logo is big and have the background color *Suggested Correction:* Standardize the logo across all login screens. Choose one logo design and delete the other screen. | Alaa Radwan | 14/Sep/24 1:36 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;15a.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10003 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Review of User Registration and login Screens – Unwanted placeholders "input field" and "button" in Background | TTP-5 | 10070 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 01:25 | 2024-09-17 22:48 | *Date:* September 14, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* Figma Design – Registration and Login Pages v1.0 *Description:* In the background of the registration and login pages, unwanted placeholder text such as "input field" and "button" is present. This text is not intended to be visible in the final design and may detract from the overall aesthetic and user experience. *Impact:* The presence of this placeholder text can confuse users and disrupt the visual clarity of the design. It may also lead to a less professional appearance and interfere with user interactions. *Suggested Correction:* Remove the unwanted placeholder text "input field" and "button" from the background of both the registration and login pages. Ensure that any background elements are purposeful and do not detract from the main content. *General Comments:* Review other similar pages or frames to ensure no unwanted text is present. Validate that the design is clean, professional, and user-friendly after making the necessary updates. | Alaa Radwan | 14/Sep/24 1:25 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;14.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10002 |  | Pre-Testing Activities | 3 | 10101 | User Account Management
Review of User Login– Inconsistent Formatting of "Given" in User Story (User Login) | TTP-3 | 10068 | Task | Done | Ton Tasks Project | software | Alaa Radwan | Medium | Done | Alaa Radwan | Alaa Radwan | Alaa Radwan | 2024-09-14 01:00 | 2024-09-17 22:48 | *Date:* September 13, 2024 *Reviewed By:* Alaa Radwan *Document Reference:* User Stories Document – v1.0 * *Issue Description:* The word "*Given*" in the sentence *"Given that the user enters their email and password"* is not bolded or colored consistently with other instances of "Given" in the user stories. * *Impact:* The inconsistent formatting may cause confusion during review or development, as it breaks the uniformity of the user story structure. * *Suggested Correction:* Bold and color the word "*Given*" to match the formatting of other "Given" instances throughout the document. The corrected sentence should be: "*Given* that the user enters their email and password," | Alaa Radwan | 14/Sep/24 1:00 AM;712020:efd86db1-5843-42c9-bdc8-cd16a09bf5fc;12.PNG;https://alaa-radwan.atlassian.net/rest/api/3/attachment/content/10000 |  | Pre-Testing Activities | 3 | 10101 | User Account Management